## Sheet1
S.No | Task Name | Task Description | ETA (in hrs)
1 | Setup project | Vite and tailwind CSS | 0.5 | Total ETA(inhrs) | 49.5
|  | Analysis | 1
2 | Shared Components | Header | 2
|  | Footer | 1
|  | Layouts | 2
3 | Reusable Components | button | 1
|  | title | 1
|  | paragraph | 1
|  | image | 1
|  | section layout | 1
4 | Pages-home | home | 2
|  | responsive | 1
|  | functions | 0.5
5 | pages-Product Listing | Product Listing(inhrs) | 2
|  | responsive | 2
|  | functions | 3
6 | pages-aboutus | aboutus | 0.5
|  | responsive | 0.5
|  | functions | 0.5
7 | pages-contactus | contactus | 1
|  | responsive | 0.5
|  | functions | 2
8 | pages-login | login | 1
|  | responsive | 1
|  | functions | 0
9 | pages-signup | signup | 1
|  | responsive | 1
|  | functions | 0
11 | pages-cart | cart | 1
|  | responsive | 1
|  | functions | 1
12 | pages-popupcart | cart | 1
|  | responsive | 1
|  | functions | 1
13 | pages-productdetails | productdetails | 1
|  | responsive | 2
|  | functions | 2
14 | pages-popupproductdetails | popupproductdetails | 1
|  | responsive | 1
|  | functions | 1
15 | pages-checkout | checkout | 1
|  | responsive | 1
|  | functions | 1
16 | pages-orderreceived | orderreceived | 0.5
|  | responsive | 0.5
|  | functions | 0.5